## Sheet1
Project: LSLforLife.com UI Test
Tester: J.D.
Date : 10/26/17
Step | Direction | Expected Outcome | Actual Outcome | Pass/Fail | Notes
1 | User navigates to http://LSLforLife.com | The LSLforLife.com splash is presented | Splash page is presented as requestd | Pass
2 | User clicks "Log in" button | The user is directed to a log in page with a username and password field. The form contains a functioning "remember me" check box | Log in page is loaded with correct form and functioning "remember me" check box | Pass
3 | User fills in incorrect log in information | The system refreshes the log in page with a "invald login" error message displayed | The page is refreshed and an invalid login error displays | Pass
4 | User fills in correct credentials | The user's home page is loaded with the appropriate home page sections displayed | The user's home page is loaded but not all sections is present | Fail | The inventory management section is missing
5 | The user selects "manage account" | The manage account page loads with a username, email, and password field. | The page is loaded as expected | Pass
6 | The user attempts to change all fields | All fields can be changed successfully | All fields can be changed successfully, but the password is not masked | Fail | We will need to change the password field to be masked